## Sheet1
Problems Encountered
Red: Issue
Yellow: Response/Actions
Green: Completed Componant
2019-01-21 | Derek told me sbout google cloud vision api
implemented google cloud vision api
2019-01-22 | Further testing with VAPI
2019-01-24 | Pi hosting FTP server is slow
2019-01-25 | FTP connection with server times out after so long
Added error handling to script
Error handling prevents script termination
Error handling refined to ensure controled termination
Automated connection and updating to server from rpi through python.
2019-01-26 | Python script for background extraction on raspberry pi takes 3 minutes to mode stack 10 images. This needs to be at most, 30 seconds as a new image will be taken every minute and should stack 30 images. This issues means such a python script is unusable.
Learning has begun for C and BASH to find a faster method of background extraction.
2019-01-28 | C++ found to be faster then C for what I wish to do {says who?}
Decision made to abandon processing on rpi so cheaper materials can be used for robot